## Sheet1
Project Name | Launch plan for Recommendation
Project Manager | Adarsh Pai
Project Deliverable | To launch
Development Start Date | 2024-01-01
Development End Date | 2024-05-09
Public Launch date | 2024-05-25
| Tasks | Responsible | Start | End | Status
Internal business
Customer Service Team | To create a new FAQ section for Recommendation feature under the Help section | Charles L | 2024-05-09 | 2015-05-14 | Complete
Customer Service Team | To train the internal and external customer service agents on the product, create SOPs for different support cases | Esteban O | 2024-05-09 | 2015-05-20 | In progress
Compliance Team | To understand the product and give sign offs after checking the required regulatory and legal constraints | Jacob S. | 2024-05-09 | 2015-05-14 | In progress
Compliance Team | To come up with any needed changes to the Terms and conditions before product launch | Daniel R | 2024-05-09 | 2015-05-14 | In progress
Operation Team | To inform and get consent from restaurants on the usage to use thier menus to create recommendations. | Siddharth B | 2024-05-01 | 2015-05-17 | Overdue
Internal tech
Devops | To ensure the servers are set up with load balancers in place to handle peak hour loads for recommendation | Frank C. | 2024-05-06 | 2015-05-10 | In progress
InfoSec | To ensure that the Api endpoints to the recommendation engine are secure against any cyber threats | Shari W. | 2024-05-01 | 2015-05-15 | Complete
On-Call Engineering | to ensure that the on-call engineers schedule has been create and ensure they are prepared to handle any issues or bugs during launch | Gautam W. | 2015-09-01 | 2015-05-15 | Complete
Marketing
PR | PR team to create the launch article and work with the different media partners such as Forbes, CBS News etc to ensure that the launch of recommendation products has good media coverage | Alex A. | 2015-05-10 | 2015-05-20 | Not started
PR | Product launch needs to be posted by all the CXO’s linkedin and media accounts. | Alex A. | 2015-05-10 | 2015-05-20 | Not started
Media | Media team to create promotional video on youtube on how the recommendation works. | Martin G. | 2015-05-17 | 2015-05-20 | In progress
Marketing | Marketing team to work on promotional and ad campaigns to build more awareness of new features. | Lewis H | 2024-05-06 | 2015-05-20 | In progress
| Launch |  | 2025-05-25 | 2025-05-25